## Slide 1
1
Year & Sem – II & III
Subject – Software Engineering (3AID4 - 07)
Unit – II
Presented by – Manju Vyas (Asst. Prof., AI&DS)
JAIPUR ENGINEERING COLLEGE AND RESEARCH CENTRE

## Slide 2
1
CONTENTS (TO BE COVERED)
UNIT II: SOFTWARE PROJECT MANAGEMENT
Introduction to Software Project Management
Key Areas of Project Management
Sample Project Life Cycle
Skills necessary for software project management
Responsibilities of a software project manager

## Slide 3
1
OBJECTIVES
The objective of software project planning is to provide a framework that enables the manager to make reasonable estimates of resources, cost, and schedule.
These estimates are made within a limited time frame at the beginning of a software project and should be updated regularly as the project progresses.
In addition, estimates should attempt to define best case and worst case scenarios so that project outcomes can be bounded.
The planning objective is achieved through a process of information discovery that leads to reasonable estimates.
In the following slides, each of the activities associated with software project planning is discussed.

## Slide 4
1
What is a project?
A project is a temporary endeavor undertaken to produce a unique product or service
What are the differences between projects and operations?
  Characteristics of Operations
    Ongoing – Continuous cycle
    Repetitive – Expected inputs and outputs
  Characteristics of Projects
    Temporary – Definitive beginning and end
    Unique – New undertaking, unfamiliar ground

## Slide 5
1
What is a successful project?
Customer Requirements satisfied/exceeded
Completed within allocated time frame
Completed within allocated budget
Acceptance by the customer

## Slide 6
1
Why do projects fail?
Poor requirements gathering
No Functional input in planning
Unrealistic planning and scheduling/Impossible schedule commitments
Lack of resources

## Slide 7
1
What is Project Management?
Project Management is the application of skills, knowledge, tools and techniques to meet the needs and expectations of stakeholders for a project
  The purpose of project management is prediction and prevention, NOT recognition and reaction
  Effective Management of the Triple Constraints
    Requirements – Needs Identified or Unidentified Expectations
    Cost/Resources – People, Money, Tools
    Schedule/Time

## Slide 8
1
Key areas of Project Management
Scope Management
Issue Management
Cost Management
Quality Management
Communications Management
Risk Management
Change Control Management

## Slide 9
1
Scope Management
Project Scope Management is the process to ensure that the project is inclusive of all the work required, and only the work require, for successful completion.
Primarily it is the definition and control of what IS and IS NOT included in the project
This component is used to communicate
  How the scope was defined
  How the project scope will be managed
  Who will manage the scope (e.g., PM, QA)
  Change Control

## Slide 10
1
Issue Management
Issues are restraints to accomplishing the deliverables of the project.
Issues are typically identified throughout the project and logged and tracked through resolution.
Issues not easily resolved are escalated for resolution.
In this section of the plan the following processes are depicted:
  Where issues will be maintained and tracked
  The process for updating issues regularly
  The escalation process

## Slide 11
1
Cost Management
The processes required to ensure the project is completed within the approved budget and includes:
  Resource Planning - The physical resources required (people, equipment, materials) and what quantities are necessary for the project
    Full Time Employees, Professional Services, Cost, and Contingency
  Budget -
    Budget estimates
    Baseline estimates
    Project Actuals

## Slide 12
1
Quality Management
Quality Management is the processes that insure the project will meet the needs via:
  Quality Planning, Quality Assurance, and Quality Control
    Clearly Defined Quality Performance Standards
    How those Quality and Performance Standards are measured and satisfied
    How Testing and Quality Assurance Processes will ensure standards are satisfied
    Continuous ongoing quality control

## Slide 13
1
Communications Management
The processes necessary to ensure timely and appropriate generation, collection, dissemination, and storage of project information using:
  Communications planning:
    Determining the needs (who needs what information, when they need it, and how it will be delivered)
  Information Distribution:
    Defining who and how information will flow to the project stakeholders and the frequency
  Performance Reporting:
    Providing project performance updates via status reporting.
Define the schedule for the Project Meetings (Team, OSC, ESC), Status Meetings and Issues Meetings to be implemented

## Slide 14
1
Risk Management
Risk identification and mitigation strategy
When\if new risks arise
Risk update and tracking

## Slide 15
1
Change Control Management
Define how changes to the projects scope will be executed
  Formal change control is required for all of the following:
    Scope Change
    Schedule changes
    Technical Specification Changes
    Training Changes
All changes require collaboration and buy in via the project sponsor’s signature prior to implementation of the changes

## Slide 16
1
Risk Management
Risk identification and mitigation strategy
When\if new risks arise
Risk update and tracking

## Slide 17
1
Sample Project Life Cycle
Initiation Phase
Definition Phase
Planning Phase
Implementation Phase
Deployment Phase
Closing Phase

## Slide 18: Initiation Phase
Define the need
Return on Investment Analysis
Make or Buy Decision
Budget Development

## Slide 19: Definition Phase
Define Project Scope
Define functional requirements
  Requirements to be prioritized into business critical and non-business critical need
Define technical requirements
Risk Management Planning

## Slide 20: Planning Phase
Resource Planning
Work Breakdown Structure
Project Schedule Development
Configuration Management Plan
Quality Assurance Plan
Production Support Plan
Service Level Agreement
System Design

## Slide 21: Implementation Phase
Training Plan
System Build
Quality Assurance

## Slide 22: Deployment Phase
User Training
Production Review
Go Live

## Slide 23: Closing Phase
Contractual Closeout
Post Production Transition
Lessons Learned

## Slide 24: Skills necessary for software project management
A theoretical knowledge of different project management techniques
Good qualitative judgment and decision taking capabilities.
Good communication skills and the ability get work done.
Skills for tracking and controlling the progress of the project, customer interaction, managerial presentations, and team building

## Slide 25: Responsibilities of a software project manager
Activities can be broadly classified:
  1. project planning, 2. project monitoring and control activities.
The project planning activity is undertaken before the development starts to plan the activities to be undertaken during development.
The project monitoring and control activities are undertaken once the development activities start with the aim of ensuring that the development proceeds as per plan and changing the plan whenever required to cope up with the situation.

## Slide 26: Project planning
Project planning is undertaken and completed even before any development activity starts.
Project planning consists of the following essential activities:
  Estimating the following attributes of the project:
    Project size: What will be problem complexity in terms of the effort and time required to develop the product?
    Cost: How much is it going to cost to develop the project?
    Duration: How long is it going to take to complete development?
    Effort: How much effort would be required?

## Slide 27
The effectiveness of the subsequent planning activities is based on the accuracy of these estimations.
  Scheduling manpower and other resources
  Staff organization and staffing plans
  Risk identification, analysis, and abatement planning
  Miscellaneous plans such as quality assurance plan, configuration management plan, etc.

## Slide 28: Precedence ordering among project planning activities

## Slide 29: Software Project Management Plan (SPMP)
Once project planning is complete, project managers document their plans in a Software Project Management Plan (SPMP) document.
Organization of the Software Project Management Plan (SPMP) Document
1.Introduction
(a) Objectives
(b) Major Functions
(c) Performance Issues
(d) Management and Technical Constraints

## Slide 30
2. Project Estimates
(a) Historical Data Used
(b) Estimation Techniques Used
(c) Effort, Resource, Cost, and Project Duration Estimates
3. Schedule
(a) Work Breakdown Structure
(b) Task Network Representation
(c) Gantt Chart Representation
(d) PERT Chart Representation

## Slide 31
4. Project Resources
(a) People
(b) Hardware and Software
(c) Special Resources
5. Staff Organization
(a) Team Structure
(b) Management Reporting
6. Risk Management Plan
(a) Risk Analysis
(b) Risk Identification
(c) Risk Estimation
(d) Risk Abatement Procedures

## Slide 32
7. Project Tracking and Control Plan
8. Miscellaneous Plans
(a) Process Tailoring
(b) Quality Assurance Plan
(c) Configuration Management Plan
(d) Validation and Verification
(e) System Testing Plan
(f) Delivery, Installation, and Maintenance Plan